## Sheet1
Task | Start Date | End Date | Duration (Days)
Research on Dataset | 2016-09-05 | 2016-09-07 | 2
Identifying Research Questions Based on Dataset | 2016-09-07 | 2016-09-15 | 8
Abstract Creation | 2016-09-15 | 2016-09-19 | 4
Research on Previous Projects with Dataset and Research Question | 2016-09-19 | 2016-09-24 | 5
Literature Review and Approach Creation | 2016-09-24 | 2016-10-10 | 16
Dataset Upload and Cleansing in R | 2016-10-10 | 2016-10-20 | 10
Formula Generation for Acceptance in US Research Universities | 2016-10-21 | 2016-10-23 | 2
Initial Regression for Acceptance Formula | 2016-10-24 | 2016-10-26 | 2
Initial Commit of Code in Github | 2016-10-26 | 2016-10-26 | 0
Additional Changes to the Code (Correlations, Variables, Formulas) for Acceptance Formula | 2016-10-27 | 2016-10-31 | 4
Formula Generation for Completion Rate in US Research Universities | 2016-10-27 | 2016-10-31 | 4
Regression for Completion Rate Formula | 2016-10-27 | 2016-10-31 | 4
Upload Changes to the Code | 2016-10-31 | 2016-11-01 | 1
Upload Initial Report (PDF and MS Word) | 2016-11-01 | 2016-11-01 | 0
Additional Regression Techniques for Both Formulas | 2016-11-01 | 2016-11-02 | 1
Upload of Changes to Code and Report | 2016-11-02 | 2016-11-03 | 1